## Sheet1
Schedule
Date |  | Event | Irie | Damiani | Hoque | Momoi | Fatmi | Yonekawa | Cai | Yamaguchi | Sano | Dai | Kobayashi | Saitoh | Ohno | Takeoka | Zanaty | Xie | NIES-G | Tohoku-U-G | Kudo (MRI) | Remarks
2019-10-15 | Tue
2019-10-16 | Wed
2019-10-17 | Thu | SKYNET CU MTG | SKYNET CU MTG
2019-10-18 | Fri | (Crisp-san's MTG@NIES) |  |  |  | (Crisp-san's MTG@NIES)
2019-10-19 | Sat
2019-10-20 | Sun
2019-10-21 | Mon | install BCM (cancelled)
2019-10-22 | Tue
2019-10-23 | Wed | install FRM samplers replace CIMEL replace PM2.5 replace a tracker | install FRM samplers replace CIMEL replace a tracker | replace a tracker | install FRM samplers | replace CIMEL | replace CIMEL | replace PM2.5 |  | replace CIMEL |  | replace a tracker | replace CIMEL | help everything(PM2.5, etc) |  |  | replace CIMEL | replace PM2.5 | install FRM samplers
2019-10-24 | Thu
2019-10-25 | Fri
2019-10-26 | Sat
2019-10-27 | Sun |  |  |  |  | JMSJ
2019-10-28 | Mon | JMSJ@Fukuoka | JMSJ | JMSJ |  | ↓ |  | JMSJ | JMSJ | JMSJ | JMSJ
2019-10-29 | Tue | ↓ | ↓ | ↓ |  | ↓ |  | ↓ | ↓ | ↓ | ↓
2019-10-30 | Wed | ↓ | ↓ | ↓ |  | ↓ |  | ↓ | ↓ | ↓ | ↓
2019-10-31 | Thu | ↓ | ↓ | ↓ |  | ↓ |  | ↓ | ↓ | ↓ | ↓
2019-11-01 | Fri
2019-11-02 | Sat
2019-11-03 | Sun
2019-11-04 | Mon
2019-11-05 | Tue | JpSAC@Aichi | JpSAC |  |  |  |  | JpSAC
2019-11-06 | Wed | ↓ | ↓ |  |  |  |  | ↓
2019-11-07 | Thu | ↓ | ↓ |  |  |  |  | ↓
2019-11-08 | Fri | [15 empty] | leave Japan
2019-11-09 | Sat
2019-11-10 | Sun
2019-11-11 | Mon | campaign preparation | PM: install BCM |  | PM: install BCM
2019-11-12 | Tue | ↓
2019-11-13 | Wed | ↓
2019-11-14 | Thu | ↓
2019-11-15 | Fri | ↓
2019-11-16 | Sat
2019-11-17 | Sun
2019-11-18 | Mon | Chiba Campaign starts 9:30 Tohoku-U-G arrives 10:00 NIES-G arrives pm: Kudo-san & Prede arrive |  |  | FRM | [13 empty] | Install FTS | Iwabuchi-sensei (day trip) Masuda-san (until Nov. 22)
2019-11-19 | Tue |  |  |  | ↓ | [14 empty] | ↓
2019-11-20 | Wed |  | 10:00- PM2.5+NO2+CO instrument setup 14:00- FLEXPART |  | ↓ |  |  |  | 14:00- FLEXPART | [9 empty] | FTS obs | ↓
2019-11-21 | Thu |  |  |  | ↓ | [14 empty] | ↓
2019-11-22 | Fri | NIES&Seoul-U visit - mtg@107 |  |  | ↓ | [13 empty] | NIES&Seoul-U visit. meeting@Rm#107. | ↓
2019-11-23 | Sat |  |  |  | ↓ | [12 empty] | leave Japan
2019-11-24 | Sun
2019-11-25 | Mon |  |  |  | ↓ | [15 empty] | E-CARE WS@Kyushu U
2019-11-26 | Tue |  |  |  | ↓ | [15 empty] | ↓
2019-11-27 | Wed |  |  |  | ↓ | [15 empty] | ↓
2019-11-28 | Thu |  |  |  | ↓ | [15 empty] | ↓
2019-11-29 | Fri |  |  |  | ↓ | [15 empty] | ↓
2019-11-30 | Sat |  |  |  | ↓
2019-12-01 | Sun |  |  |  | ↓
2019-12-02 | Mon | Chiba Campaign ends |  |  | ↓
2019-12-03 | Tue | possible extension of or closing the campaign
2019-12-04 | Wed | G2AERO study MTG@CEReS (10-12) | G2AERO study MTG | [15 empty] | G2AERO study MTG
2019-12-05 | Thu
2019-12-06 | Fri
2019-12-07 | Sat
2019-12-08 | Sun | AGU | AGU | AGU |  | AGU |  | AGU |  | AGU
2019-12-09 | Mon | ↓ | ↓ | ↓ |  | ↓ |  | ↓ |  | ↓
Daily task (*responsible person) |  |  |  |  | FRM | everything (help all) | analysis & sensitivity study for SR | M論 | FLEXPART analysis & sensitivity study for SR | POM-02 data plot (AOD, AAOD, AE, AAE, ...) BC, PM2.5, BC/PM2.5 analysis & sensitivity study for SR | FTS GOSAT-2 | Plot (solar radiation) MODIS & GCOM-C data analysis (& sky radiometer) | AERONET (sun&lunar)+sky radiometer SR-CEReS analysis & sensitivity study for SR | Plot: NO2 (4Z-MAXDOAS, TROPOMI) | (MWR? PM2.5?) | (MWR? PM2.5?) |  | whole-sky camera or skyview