## Sheet1
Schedule
Date |  | Event | Irie | Damiani | Momoi | Fatmi | Cai | Yamaguchi | Sano | Xue | Dai | Kobayashi | Saitoh | Nishiwaki | Ohno | Takeoka | NIES-G | Tohoku-U-G | Kudo (MRI) | Remarks
2020-11-16 | Mon
2020-11-17 | Tue | B4 presentation
2020-11-18 | Wed | arrival of MS700 | [8 empty] | test MS700
2020-11-19 | Thu
2020-11-20 | Fri
2020-11-21 | Sat
2020-11-22 | Sun
2020-11-23 | Mon
2020-11-24 | Tue | GEMS WS | (GEMS WS)
2020-11-25 | Wed | install NIES samplers (FRMs) | install NIES samplers (FRMs) | [13 empty] | install NIES samplers (FRM) (Fujitani-san)
2020-11-26 | Thu | arrival of Li-7810 install MS700 | start using Li-7810 install MS700 | [5 empty] | start using Li-7810 |  | Install MS-700 |  |  |  | start using Li-7810
2020-11-27 | Fri
2020-11-28 | Sat
2020-11-29 | Sun
2020-11-30 | Mon | Chiba Campaign starts | filter replacement |  |  |  |  | FTS support | [8 empty] | 11:00- EM27/SUN設置(Morino-san's group) |  |  | 11:00 Takase-san(TUS) arrives
2020-12-01 | Tue |  | ↓
2020-12-02 | Wed |  | ↓
2020-12-03 | Thu |  | ↓
2020-12-04 | Fri |  | ↓
2020-12-05 | Sat
2020-12-06 | Sun
2020-12-07 | Mon |  | ↓
2020-12-08 | Tue |  | ↓
2020-12-09 | Wed |  | ↓
2020-12-10 | Thu |  | ↓
2020-12-11 | Fri |  | ↓
2020-12-12 | Sat
2020-12-13 | Sun | Chiba Campaign ends
2020-12-14 | Mon |  | filter replacement | [13 empty] | remove NIES samplers (FRMs)
Daily task (*responsible person) |  |  | filter replacement forNIES samplers (FRM) | support | support | support skyradiometer(sens. test) | support | FTS daily report (AAE, AAOD, etc.)? | LiCOR CH4(Li-7810) daily report? | Himawari-8 daily report? | MS700, PAR, global solar radiation daily report | skyradiometer daily report | MAX-DOAS TROPOMI daily report | LP-DOAS visibility meter daily report (as often as possible) | LiCOR CH4/CO2/H2O Skyradiometer MAX-DOAS (FTS) daily report (LI-7810, etc.?) | H2O daily report (H2O?)